## Project Schedule
PROJECT SCHEDULE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Healthcare System Project | Tyler Butler | 2019-02-06 | 2019-04-30 |  | 10% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 2019-02-06 | 2019-02-28 | 22 | In progress
| Feature 1 |  | Tyler B. | 2019-02-06 | 2019-02-28 | 22 | In progress
| Feature 2 |  | Jonathan A. | 2019-02-06 | 2019-02-28 | 22 | In progress
| Feature 3 |  | Xue L. | 2019-02-06 | 2019-02-28 | 22 | In progress
| Feature 4 |  | Jeremy B. | 2019-02-06 | 2019-02-28 | 22 | In progress
| Sprint 2 |  |  | 2019-03-01 | 2019-03-31 | 31 | Not started
| Feature 5 |  | Tyler B. | 2019-03-01 | 2019-03-31 | 31 | Not started
| Feature 6 |  | Jonathan A. | 2019-03-01 | 2019-03-31 | 31 | Not started
| Feature 7 |  | Xue L. | 2019-03-01 | 2019-03-31 | 31 | Not started
| Feature 8 |  | Jeremy B. | 2019-03-01 | 2019-03-31 | 31 | Not started
| Sprint 3 |  |  | 2019-04-01 | 2019-04-30 | 30 | Not started
| Feature 9 |  | Tyler B. | 2019-04-01 | 2019-04-30 | 30 | Not started
| Feature 10 |  | Jonathan A. | 2019-04-01 | 2019-04-30 | 30 | Not started
| Feature 11 |  | Xue L. | 2019-04-01 | 2019-04-30 | 30 | Not started
| Feature 12 |  | Jeremy B. | 2019-04-01 | 2019-04-30 | 30 | Not started